## Design Bid Build
Cal Poly Facilities Planning / Facility Services Capital Project Review Matrix
for Design / Bid / Build Projects
Design Stage | Focus | Plans | Spec Divisions (1995 Master Format) | Internal Reviewers | [18 empty] | External Reviewers/Other Requirements
|  |  |  | Director | Asst Director, Engineering | Asst Director, Landscape | Asst Director, Custodial | Mgr Arch Trades | Mgr Engineering and Utilities | Mgr Grounds | Engineering Supervisor | Electric Supervisor | Plumbing Supervisor | Carpenter Supervisor | Paint Supervisor | Custodial Supervisors | Control Specialist | Telecomm Mgr | Telecomm Specialist | Media Disribution Services Manager | Media Distribution Services Technician | Landscape Advisory Committee
Programming | M, E, P, Utilities | [21 empty] | Campus Standards to design team
Telecomm
Schematic Kickoff | M, E, P, Utilities | [21 empty] | Siemens
| Telecomm | [21 empty] | Savings by Design Application
100% Schematic | Mechanical | M | 2, 14, 15 | [19 empty] | Mechanical Review Board
| Electrical | E, HVE | 2, 16 | [19 empty] | Seismic Review Board
| Plumbing | P, M | 2, 15 | [19 empty] | Commissioning Agent
| Site Utilities | M, P, E, C, L, T | 2, 15, 16 | [19 empty] | Chancellor's Office CPDC
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12 | [19 empty] | Savings by Design
| Structural | S | [20 empty] | Apps for new utility service
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
50% PD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Commissioning Agent
| Plumbing | P, M | 2, 15 | [19 empty] | State Fire Marshal
| Site Utilities | M, P, E, C, L, T | 2, 15, 16 | [19 empty] | Plan Check
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
| Structural | S
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
100% PD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Commissioning Agent
| Plumbing | P, M | 2, 15 | [19 empty] | Chancellor's Office CPDC
| Site Utilities | M, P, E, C, L, T | 2, 15, 16
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
| Structural | S
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
50% CD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Mechanical Review Board
| Plumbing | P, M | 2, 15 | [19 empty] | Commissioning Agent
| Site Utilities | M, P, E, C, L, T | 2, 15, 16
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
| Structural | S
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
95% CD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Seismic Review Board
| Plumbing | P, M | 2, 15 | [19 empty] | Commissioning Agent
| Site Utilities | M, P, E, C, L, T | 2, 15, 16 | [19 empty] | State Fire Marshal
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12 | [19 empty] | DSA
| Structural | S | [20 empty] | Plan Check
| Custodial | A | 2, 9, 10, 12, 15 | [19 empty] | Chancellor's Office CPDC
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
100% CD | All | All | All | [19 empty] | Chancellor's Office CPDC
Director's signoff | All |  | Complete comment log with disposition
Submittals/Change Orders | Mechanical | 13420 or 15120 | Flow meters
|  | 14200 | Elevators
|  | 15120 | Pipe Expansion Joints
|  | 15900 | Control System
|  | 16260 | Variable Frequency Drives
| Plumbing | 15190 | Flush valves and sensor faucets
| Electrical | 16428 | Pad mounted switchgear
|  | 16470 | Panel Boards
|  | 16480 | Motor Control Centers
|  | 16496 | Generator Set and Transfer Switch
| Architectural | 8710 | Door hardware
|  | 8740 | Electro-mechanical door hardware
|  | 9900 | Paints and coatings
| Custodial | 6415 | Countertops
|  | 6600 | Solid surface countertops
|  | 9300 | Tile and grout
|  | 12300 | Integral sink and countertop
|  | 15410 | Waterless urinals
| Site/Landscape | 2810 | Irrigation controls
| Telecomm |  | All equipment

## Design Build
Cal Poly Facilities Planning / Facility Services Capital Project Review Matrix
for Design Build Projects
Design Stage | Focus | Plans | Spec Divisions (1995 Master Format) | Internal Reviewers | [18 empty] | External Reviewers/Other Requirements
|  |  |  | Director | Asst Director, Engineering | Asst Director, Landscape | Asst Director, Custodial | Mgr Arch Trades | Mgr Engineering and Utilities | Mgr Grounds | Engineering Supervisor | Electric Supervisor | Plumbing Supervisor | Carpenter Supervisor | Paint Supervisor | Custodial Supervisors | Control Specialist | Telecomm Mgr | Telecomm Specialist | Media Disribution Services Manager | Media Distribution Services Technician | Landscape Advisory Committee
Programming | M, E, P, Utilities | [21 empty] | Campus Standards to design team
Telecomm
Schematic Kickoff | M, E, P, Utilities | [21 empty] | Siemens
| Telecomm | [21 empty] | Savings by Design Application
50% RFP | Mechanical | M | 2, 14, 15 | [19 empty] | Mechanical Review Board
| Electrical | E, HVE | 2, 16 | [19 empty] | Seismic Review Board
| Plumbing | P, M | 2, 15 | [19 empty] | Commissioning Agent
| Site Utilities | M, P, E, C, L, T | 2, 15, 16 | [19 empty] | Chancellor's Office CPDC
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
| Structural | S
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
100% RFP | Mechanical | M | 2, 14, 15 | [19 empty] | Mechanical Review Board
| Electrical | E, HVE | 2, 16 | [19 empty] | Seismic Review Board
| Plumbing | P, M | 2, 15 | [19 empty] | Commissioning Agent
| Site Utilities | M, P, E, C, L, T | 2, 15, 16 | [19 empty] | Chancellor's Office CPDC
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12 | [19 empty] | Savings by Design
| Structural | S | [20 empty] | Apps for new utility service
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
50% PD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Commissioning Agent
| Plumbing | P, M | 2, 15 | [19 empty] | State Fire Marshal
| Site Utilities | M, P, E, C, L, T | 2, 15, 16 | [19 empty] | Plan Check
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
| Structural | S
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
100% PD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Commissioning Agent
| Plumbing | P, M | 2, 15 | [19 empty] | Chancellor's Office CPDC
| Site Utilities | M, P, E, C, L, T | 2, 15, 16
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
| Structural | S
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
50% CD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Mechanical Review Board
| Plumbing | P, M | 2, 15 | [19 empty] | Commissioning Agent
| Site Utilities | M, P, E, C, L, T | 2, 15, 16
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
| Structural | S
| Custodial | A | 2, 9, 10, 12, 15
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
95% CD | Mechanical | M | 2, 14, 15 | [19 empty] | Siemens
| Electrical | E, HVE | 2, 16 | [19 empty] | Seismic Review Board
| Plumbing | P, M | 2, 15 | [19 empty] | Commissioning Agent
| Site Utilities | M, P, E, C, L, T | 2, 15, 16 | [19 empty] | State Fire Marshal
| Architectural | A | 3, 4, 5, 6, 7, 8, 9, 10, 11, 12 | [19 empty] | DSA
| Structural | S | [20 empty] | Plan Check
| Custodial | A | 2, 9, 10, 12, 15 | [19 empty] | Chancellor's Office CPDC
| Site/Landscape | C, L | 2, 3
| Telecomm | E, T | 11, 16
100% CD | All | All | All | [19 empty] | Chancellor's Office CPDC
Director's signoff | All |  | Complete comment log with disposition
Submittals/Change Orders | Mechanical | 13420 or 15120 | Flow meters
|  | 14200 | Elevators
|  | 15120 | Pipe Expansion Joints
|  | 15900 | Control System
|  | 16260 | Variable Frequency Drives
| Plumbing | 15190 | Flush valves and sensor faucets
| Electrical | 16428 | Pad mounted switchgear
|  | 16470 | Panel Boards
|  | 16480 | Motor Control Centers
|  | 16496 | Generator Set and Transfer Switch
| Architectural | 8710 | Door hardware
|  | 8740 | Electro-mechanical door hardware
|  | 9900 | Paints and coatings
| Custodial | 6415 | Countertops
|  | 6600 | Solid surface countertops
|  | 9300 | Tile and grout
|  | 12300 | Integral sink and countertop
|  | 15410 | Waterless urinals
| Site/Landscape | 2810 | Irrigation controls
| Telecomm |  | All equipment