# Facility Services

# Procedural Guidelines

Title: Inspection of Major Capital Projects

Creation Date: 10/23/2007		Revision Date: 8/24/2009		From: Mark Hunter

This procedure will provide an inspection structure by which Facility Services staff is afforded input on major capital projects during the construction phase.

# Preparation:

- Staff who intend to inspect, must adhere to all project rules, regulations, and procedures as advised by the Facilities Planning Project Manager.  These might include but are not limited to:

  - Safety orientation.

  - Personal Protective Equipment.

# Schedule:

- Inspection Consultant will notify Facilities Planning at least one (1) week in advance of any proposed inspection.

- Facilities Planning will notify the Executive Director for Facility Services at least one (1) week in advance of proposed inspection.

- Notification will include areas available for inspection, by trade.

- Inspections will focus on critical phases of the project:

  - Concrete pours prior to pouring concrete.

  - Framing inspections.

  - MEP rough-in.

  - Walls and ceilings prior to closure.

  - Mechanical, electrical, telecommunications, custodial room, etc., completions.

  - Punch list Inspection.

  - Other inspections as requested or required.

  - Inspection will be scheduled for a specific day and time.

  - Any “make-up” inspections are discouraged, and must be approved by the Project Manager.

# Report:

- All comments are to be forwarded to the Executive Director for Facility Services within three (3) working days of the inspection.

- Assistant Director will forward one compiled and complete list to the Project Manager, with copies to Associate Director of Facility Planning for Construction and the Project Inspector.

- Facilities Planning, in conjunction with their consultants, shall provide a written framework for the inspection.

The Project Manager will return findings on all comments no later than twenty (20) working days:

- Changes will be made per contract.

- Requests or comments not in contract scope.

- Other.

- Facilities Planning is responsible for forwarding all comments to the Consulting Inspector.

# Representation:

- Shops to be invited, depending upon phase and installation, include but are not limited to:

  - Electric

  - Plumbing

  - Carpentry

  - Paint

  - Engineering

  - Landscape

  - Custodial

  - Locks

  - Inspector

  - It is the responsibility of each Shop Supervisor to attend or designate a representative to attend.

  - Up to two attendees per shop.

  - Facility Services personnel are to take care to provide no direction to contractors.  All input is to be provided via e-mail to Executive Director for Facility Services.

  - Inspections will always include a representative of the Inspection Consultant, the contractor, and Facilities Planning.

  - It is the responsibility of Facility Service to decide what representatives to send to the inspection, depending upon the information provided by Consultant.